## Tasks
The table below shows the raw historical data - our user stories.
Each time a story's state changes we add another line to represent the new state.
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | Title | Valid from | Estimate | Is done? | Work done | Comment
RG-1 | Learn/ brush up on React/Node.js/Docker | 2022-01-11 | 1 | 1 | 1
RG-2 | Find and familiarize ourselves with a recipe API | 2022-01-11 | 1 | 1 | 1
RG-3 | Initial database setup in a docker container | 2022-01-11 | 1 | 1 | 1
RG-4 | Create basic workflow of the frontend | 2022-01-11 | 2 | 0 | 1
RG-5 | Design mockups of the webpage | 2022-01-11 | 1 | 1 | 1

## Burn-up
This is the data for a simple burn-up chart. It is based on the raw historical data in the previous sheet.
The important function is sumValid (cell B11 and also C11), defined in the script associated with this spreadsheet.
This calculates the relevant data points for the given dates, based on the history of changed data.
First param: Date for a chart's data point (on its x-axis). Any data that was valid on this date will summed.
Second param: Table of historic data, including header row. It must have columns for the ID, the date it's valid from, and of course the data itself (e.g. the story size)
Third param: The name of the column with the ID. As a data item changes over time the ID should stay the same.
Fourth param: Name of the column with the date that the data is valid from.
Fifth param: Name of the column with the data to be summed.
Date | Ideal Work | Work done
2022-01-11 | 1 | 0
2022-01-13 | 2 | 1
2022-01-15 | 3 | 1
2022-01-17 | 4 | 3
2022-01-19 | 5 | 4
2022-01-21 | 6 | 5