## Tasks
The table below shows the raw historical data - our user stories.
Each time a story's state changes we add another line to represent the new state.
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | Title | Valid from | Estimate | Is done? | Work done | Comment
RG-57 | Create component to search API and display results | 2022-02-02 | 3 | 1 | 3
RG-64 | Create database schema for user's recipes and grocery lists | 2022-02-02 | 3 | 1 | 3
RG-68 | Create server endpoints to create new grocery lists and view created lists | 2022-02-02 | 2 | 1 | 2
RG-69 | Create user interface to add recipes to user's favorite recipes | 2022-02-02 | 2 | 1 | 2
RG-72 | Create server endpoint to add and view recipes to user's favorite recipes | 2022-02-02 | 4 | 1 | 4
RG-73 | Create a frontend component that displays the recipes in detail. | 2022-02-02 | 2 | 1 | 2
RG-74 | Make Mobile Background | 2022-02-02 | 1 | 1 | 1
RG-75 | Create meal calendar frontend component | 2022-02-02 | 5 | 1 | 5
RG-77 | Improve website style/scaling across various pages | 2022-02-02 | 4 | 1 | 4
RG-78 | Create front page searchbar interface to take and forward user queries to search component | 2022-02-02 | 3 | 1 | 3
RG-70 | Create grocery list page | 2022-02-02 | 4 | 0 | 1
RG-65 | Create user interface/page to view user's favorite recipes | 2022-02-02 | 3 | 1 | 3

## Burn-up
This is the data for a simple burn-up chart. It is based on the raw historical data in the previous sheet.
The important function is sumValid (cell B11 and also C11), defined in the script associated with this spreadsheet.
This calculates the relevant data points for the given dates, based on the history of changed data.
First param: Date for a chart's data point (on its x-axis). Any data that was valid on this date will summed.
Second param: Table of historic data, including header row. It must have columns for the ID, the date it's valid from, and of course the data itself (e.g. the story size)
Third param: The name of the column with the ID. As a data item changes over time the ID should stay the same.
Fourth param: Name of the column with the date that the data is valid from.
Fifth param: Name of the column with the data to be summed.
Date | Ideal Work | Work done
2022-03-08 | 6 | 0
2022-03-11 | 12 | 2
2022-03-14 | 18 | 8
2022-03-17 | 24 | 13
2022-03-20 | 30 | 25
2022-03-23 | 36 | 33