## Tasks
The table below shows the raw historical data - our user stories.
Each time a story's state changes we add another line to represent the new state.
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | Title | Valid from | Estimate | Is done? | Work done | Comment
RG-65 | Create grocery list page | 2022-02-24 | 3 | 1 | 5
RG-70 | Create user interface/page to view user's favorite recipes | 2022-02-28 | 3 | 1 | 3
RG-76 | Create server endpoints to plan recipes in a dynamic meal calendar | 2022-02-28 | 3 | 1 | 3
RG-79 | Get calendar events connected to buttons | 2022-02-28 | 3 | 1 | 3
RG-80 | Get search bar looking ok/featured cards all same size | 2022-02-28 | 2 | 1 | 2
RG-81 | Connect calendar events to backend | 2022-02-28 | 5 | 1 | 3
RG-82 | Create add to calendar function | 2022-02-28 | 2 | 1 | 2
RG-83 | Redesign Background (backlog) | 2022-02-28 | 1 | 1 | 1
RG-65 | Create grocery list page | 2022-02-28 | 5 | 1 | 1
RG-85 | Create functionality to add grocery lists | 2022-02-28 | 3 | 1 | 3
RG-84 | Create functionality to delete grocery lists | 2022-02-28 | 3 | 1 | 3
RG-86 | Create interface for adding ingredients to a grocery list | 2022-02-28 | 3 | 1 | 3

## Burn-up
This is the data for a simple burn-up chart. It is based on the raw historical data in the previous sheet.
The important function is sumValid (cell B11 and also C11), defined in the script associated with this spreadsheet.
This calculates the relevant data points for the given dates, based on the history of changed data.
First param: Date for a chart's data point (on its x-axis). Any data that was valid on this date will summed.
Second param: Table of historic data, including header row. It must have columns for the ID, the date it's valid from, and of course the data itself (e.g. the story size)
Third param: The name of the column with the ID. As a data item changes over time the ID should stay the same.
Fourth param: Name of the column with the date that the data is valid from.
Fifth param: Name of the column with the data to be summed.
Date | Total Work | Work done
2022-02-21 | 32 | 2
2022-02-23 | 32 | 5
2022-02-25 | 32 | 9
2022-02-27 | 32 | 12
2022-03-01 | 32 | 17
2022-03-03 | 32 | 25
2022-03-05 | 32 | 28
2022-03-08 | 32 | 32